# Wellness Water Company — Publishing Checklist & 6-Month Content Calendar

## Rollout Plan for the 25 Pillar Articles

Companion to `WellnessWater-25-Pillar-Blog-Content.md` and `WellnessWater-Citations-and-Infographic-Briefs.md`. This is the operational plan: what to do before launch, the repeatable checklist for every post, the week-by-week calendar, the internal-linking map, and the KPIs to track.

## PART 1 — ONE-TIME PRE-LAUNCH SETUP (do this first)

Complete these once before publishing Article #1. They make every later post rank faster.

- [ ] Confirm SEO plugin (Yoast or Rank Math) is installed and configured; enable XML sitemap.

- [ ] Create a `/blog/` hub (or use the existing one) that links to all clusters.

- [ ] Set up 5 cluster category pages (Contaminants, Hard Water, Buying Guides, Health & Family, Technology & Trust) so articles roll up to a topic hub.

- [ ] Map internal links to money pages: Whole-House Filtration, Water Softeners, Reverse Osmosis/Drinking, combo system, and the free-water-test/contact page.

- [ ] Resolve legacy/duplicate URLs found in the sitemap (the -old, duplicate-, and test pages) — 301-redirect or noindex them so they don't dilute authority.

- [ ] Add Organization + LocalBusiness schema site-wide, and an author/reviewer profile for Dr. Ronald Sidney Stuart, M.D. (links from health-article review stamps).

- [ ] Create the "free water test" lead form and a zip-code lookup if possible, to embed in high-intent posts.

- [ ] Set up tracking: Google Search Console, GA4 goals for water-test form submits and calls, and rank tracking for the 25 focus keywords.

- [ ] Prepare the brand-claim proof points (NASA-grade tech, lifetime warranty, certifications, physician on team) so they can be cited consistently.

## PART 2 — THE PER-ARTICLE PUBLISHING CHECKLIST (repeat for all 25)

Use this exact checklist every time you publish one of the pillars.

### A. Content & On-Page

- [ ] Paste the body; confirm a single H1 distinct from the SEO Title.

- [ ] Enter SEO Title, Slug, Meta Description, and Focus Keyword (from the article's SEO block) into the SEO plugin.

- [ ] Confirm focus keyword appears in: H1, first 100 words, one H2, URL, meta title, and one image alt.

- [ ] Add the Key Takeaways box near the top.

- [ ] Confirm the FAQ section is present and questions are phrased naturally (for People Also Ask).

- [ ] Add the CTA in intro, mid-article, and conclusion (free water test).

### B. Citations & E-E-A-T

- [ ] Verify the inline citation hyperlinks resolve (already added on key stats); add any remaining links from the Citations doc on the recommended anchor text.

- [ ] For health articles (#1, #4, #5, #10, #16, #17): apply the "Medically reviewed by Dr. Ronald Sidney Stuart, M.D." stamp + today's date.

- [ ] Add an author byline + bio.

### C. Schema

- [ ] Add Article (or BlogPosting) + FAQPage.

- [ ] Add HowTo on process posts (#2, #3, #8, #21, #24).

- [ ] Add MedicalWebPage w/ reviewedBy on health posts (#1, #4, #5, #10, #16, #17).

- [ ] Add Product/Offer where a system is featured (#11, #14, #23).

### D. Media & Core Web Vitals

- [ ] Add the hero infographic (from the design brief); export WebP, set the specified alt text + file name, define width/height.

- [ ] Compress images; lazy-load below-the-fold; confirm LCP image is preloaded.

- [ ] Mobile check: short paragraphs, tappable CTA buttons, click-to-call.

### E. Internal Linking

- [ ] Link to 3–6 sibling pillars in the same cluster (see Part 4 map).

- [ ] Link to the cluster's money page with descriptive anchor text.

- [ ] Update older/existing blog posts to link up to this new pillar.

- [ ] For map posts (#6, #25): link to relevant state/city service pages.

### F. Publish & Promote

- [ ] Add to XML sitemap; request indexing in Search Console.

- [ ] Add a clickable table of contents on 3,000+ word posts.

- [ ] Share to email list + social; for #6 and #25, add an embed/share snippet to earn backlinks.

- [ ] Log publish date + target keyword in the tracking sheet.

## PART 3 — THE 6-MONTH EDITORIAL CALENDAR

Cadence: ~1 article/week (a sustainable pace for quality + indexing). Front-load the highest commercial-intent and link-bait pieces. Adjust to your team's capacity.

### Month 1 — Commercial intent + first link magnet

| Week | Article | Why now |
| --- | --- | --- |
| 1 | #11 Whole-House Filtration Cost | Highest buyer intent — captures ready-to-buy searches first |
| 2 | #1 PFAS Forever Chemicals | High-volume, high-trust topic; anchors the contaminant hub |
| 3 | #6 Hard Water Map of America | Flagship link-bait asset; start earning backlinks early |
| 4 | #13 How to Choose a Water Company | Converts comparison shoppers; strong trust play |

### Month 2 — Buyer decision cluster

| Week | Article | Why now |
| --- | --- | --- |
| 5 | #12 RO vs. Whole-House | Resolves the #1 buyer confusion |
| 6 | #7 True 10-Year Cost of Hard Water | Drives softener demand; pairs with #6 |
| 7 | #15 City Water vs. Well Water | Segments the audience; feeds many later posts |
| 8 | #14 Tankless RO Buyer's Guide | Promotes the drinking-water product line |

### Month 3 — Contaminant authority (E-E-A-T)

| Week | Article | Why now |
| --- | --- | --- |
| 9 | #3 Well Water Testing Guide | Owns the well-owner segment |
| 10 | #5 Heavy Metals (Arsenic/Lead/etc.) | High-trust, citation-rich |
| 11 | #2 Reading Your Water Report (CCR) | Practical, links to the free test |
| 12 | #4 Microplastics | Trending, shareable, RO tie-in |

### Month 4 — Hard water depth + first health piece

| Week | Article | Why now |
| --- | --- | --- |
| 13 | #9 Salt-Free Conditioners (TAC) | Resolves a major softener debate |
| 14 | #8 Limescale Explained | Supports the softener funnel |
| 15 | #10 Hard Water, Skin & Hair | First health-review piece; broad appeal |
| 16 | #22 Certifications (NSF/ANSI) | Builds buying confidence |

### Month 5 — Technology, trust & retention

| Week | Article | Why now |
| --- | --- | --- |
| 17 | #23 NASA-Grade Technology | Showcases the brand differentiator |
| 18 | #24 Installation: What to Expect | Removes a purchase objection |
| 19 | #21 Maintenance Schedule | Retention + supports existing customers |
| 20 | #16 Water Quality & Health | Top-funnel, physician-reviewed |

### Month 6 — Lifestyle reach + regional hub

| Week | Article | Why now |
| --- | --- | --- |
| 21 | #17 Safe Water for Babies & Pregnancy | High emotional intent; physician-reviewed |
| 22 | #18 Bottled vs. Filtered | Shareable, cost-driven conversion |
| 23 | #20 Best Water for Coffee/Tea/Cooking | Lifestyle, link-worthy |
| 24 | #19 Filtered Water for Pets | Light, shareable, broad reach |
| 25 | #25 U.S. Water Quality by Region | Flagship hub; internal-links to all city/state pages — publish last to tie everything together |

Faster option: to publish in ~3 months, run 2 articles/week and keep the same order. Don't sacrifice the infographic + citation steps for speed — they're what makes these outrank generic competitors.

## PART 4 — INTERNAL LINKING MAP (hub-and-spoke)

Each cluster funnels authority to a money page. Link siblings to each other and up to the anchor.

| Cluster | Articles | Anchor money page(s) |
| --- | --- | --- |
| A — Contaminants | 1, 2, 3, 4, 5 | Whole-House Filtration + Free Water Test |
| B — Hard Water | 6, 7, 8, 9, 10 | Water Softeners |
| C — Buyer Decisions | 11, 12, 13, 14, 15 | All product pages + Contact/Quote |
| D — Health & Family | 16, 17, 18, 19, 20 | Reverse Osmosis / Drinking Water |
| E — Technology & Trust | 21, 22, 23, 24, 25 | Our Products, Our Team, Warranty |

Cross-cluster links that matter most:

- #1 PFAS, #5 Heavy Metals, #4 Microplastics → all link to #14 Tankless RO and the RO product (RO is the removal solution).

- #6 Hard Water Map ↔ #7 Cost ↔ #8 Limescale ↔ #9 Salt-Free ↔ #10 Skin/Hair (tight softener cluster).

- #11 Cost, #12 RO vs Whole-House, #13 Choose a Company → link to each other (the decision trio).

- #6 and #25 (maps) → link out to state/city service pages and to the free water test.

- Every article → at least one link to the free water test / contact page.

## PART 5 — KPIs & REVIEW CADENCE

Track per article (in Search Console + GA4):

- Impressions & average position for the focus keyword (and secondary keywords).

- Clicks / organic sessions.

- Featured snippet / People-Also-Found / AI Overview appearances.

- Engagement: scroll depth, time on page.

- Conversions: free-water-test form submits and calls attributed to the post.

Review schedule:

- 30 days post-publish: confirm indexing, check initial rankings, fix any technical issues.

- 90 days: assess ranking trajectory; add internal links from newer posts; expand thin sections if stuck on page 2.

- Every 6–12 months: refresh stats and "Last updated" date; re-confirm citations; update the medical-review date on health posts.

Quick wins to watch for:

- Posts ranking positions 5–15 → add internal links + tighten the intro answer to push onto page 1.

- Posts earning impressions but few clicks → rewrite the meta title/description for click-through.

- High-traffic posts → add or strengthen the in-content lead form.

This plan assumes ~1 post/week. The order prioritizes revenue (buyer-intent posts first), then authority (contaminant + hard-water clusters), then reach (lifestyle), closing with the regional hub that ties the internal-link structure together.